## Milestones
Milestone | Description | Build estimate | Tasks done % | Target start | Target launch | Status | Notes
M0 — Repo clean-up | Clean codebase & GitHub; everything on Rituja; clean git status | 20% | 8% | 2026-06-30 | 2026-07-10 | In progress | Gate: all M1 work blocked until this is done
M1 — MVP launch | Existing full plan, stabilized & legally launchable, free | 70% | 5% | 2026-06-30 | 2026-07-25 | In progress | Internally ready ~25 Jul; folds into the 15 Aug public launch
M2 — Full product | M1 + freemium 10-minute emergency wedge | 35% | 0% | 2026-07-28 | 2026-08-15 | Not started | PUBLIC LAUNCH 15 Aug (Independence Day). Date-driven: cut scope, not the date
M3 — Version 2 | Person/child/role redesign, multi-child, subscription infra | 10% | 0% | 2026-09-01 | 2026-10-24 | Design locked | Post-launch track; 8 phases; Razorpay deferred until pricing turns on

## Tasks
Milestone | Ref | Task | Detail | Type | Effort | Launch gate | 15-Aug scope | Status | % Complete | Owner | Start date | Due date | Done date | Depends on | Notes
M0 | M0-1 | Relaunch Claude from GitProjectRituja | Exit current session; relaunch from C:\LegacyNest\Git\GitProjectRituja\legacynest so cwd, preview & scratchpad are all Rituja | Ops | S | Yes | Yes | Not started | 0% |  | 2026-07-10
M0 | M0-2 | Verify all commits belong to Rituja | Confirm git log & remote point to ritujaganguly-cmyk/legacynest only | Ops | S | Yes | Yes | Not started | 0% | 2026-06-30 | 2026-07-10
M0 | M0-3 | Remove remaining Ganguly80 hardcoded paths | Scan & fix any remaining GitProjectGanguly80 paths in source files | Eng | S | Yes | Yes | In progress | 50% | 2026-06-30 | 2026-07-10
M0 | M0-4 | Run migrations 048-051 on live Supabase | Apply all pending migrations; verify every module loads/saves live | Ops | S | Yes | Yes | Not started | 0% | 2026-06-30 | 2026-07-10 |  | M1-1
M0 | M0-5 | Commit or discard all dirty/generated files | routeTree.gen.ts and any untracked files — clean git status | Ops | S | Yes | Yes | Not started | 0% | 2026-06-30 | 2026-07-10
M0 | M0-6 | Confirm clean build on Rituja | npm run build succeeds with zero errors from GitProjectRituja | QA | S | Yes | Yes | Not started | 0% | 2026-07-08 | 2026-07-10 |  | M0-3,M0-5
M1 | M1-1 | Run migrations 048-051 on live Supabase | Apply pending migrations and confirm every module loads/saves live | Ops | S | Yes | Yes | In progress | 40% |  | 2026-06-30 | 2026-07-02
M1 | M1-2 | Full module QA pass | Each section: create / edit / delete / reload verified live | QA | M | Yes | Yes | Not started | 0% |  | 2026-07-01 | 2026-07-09
M1 | M1-3 | Emergency reliability hardening | No silent catches, idempotent activation, E2E checklist (REDESIGN_PLAN 13.1) | Eng | M | Yes | Yes | Not started | 0% |  | 2026-07-07 | 2026-07-11 |  | M1-1
M1 | M1-4 | Auth hardening | Real signup + email verification; remove silent auto-provision | Eng | M | Yes | Yes | Not started | 0% |  | 2026-07-14 | 2026-07-18
M1 | M1-5 | Terms of Service + Privacy Policy pages | DPDP / SPDI compliant public legal pages (start early - external turnaround) | Legal | S | Yes | Yes | Not started | 0% |  | 2026-06-30 | 2026-07-18
M1 | M1-6 | Error monitoring | Surface failures instead of silent safe() fallbacks; basic logging | Eng | S | No | Yes | Not started | 0% |  | 2026-07-21 | 2026-07-22
M1 | M1-7 | Mobile / responsive pass | Verify key flows on mobile viewport | UI | S | No | Yes | Not started | 0% |  | 2026-07-23 | 2026-07-25
M1 | M1-8 | Confirm Supabase backups (PITR) | Point-in-time recovery enabled before real user data lands | Ops | S | Yes | Yes | Not started | 0% |  | 2026-06-30 | 2026-07-01
M2 | M2-1 | Emergency page redesign - 4 break-glass blocks | daily_care / medical / financial / legal blocks (REDESIGN_PLAN 5.1) | Product | M | No | Yes | Not started | 0% |  | 2026-07-28 | 2026-08-01
M2 | M2-4 | Restructure landing | Quick emergency path vs full plan | UI | S | No | Yes | Not started | 0% |  | 2026-07-28 | 2026-07-30
M2 | M2-2 | 10-minute free onboarding flow | Dependent -> 4 blocks -> 1-2 coordinators -> ready | Product | M | No | Yes | Not started | 0% |  | 2026-08-04 | 2026-08-08
M2 | M2-3 | "You're ready" wallet card | jspdf/html2canvas, minimal PII, QR -> tokenized URL (first to cut if slipping) | Product | M | No | Yes | Not started | 0% |  | 2026-08-07 | 2026-08-11
M2 | M2-5 | Free-flow time instrumentation | Track time-to-complete; alert if > 12-15 min (first to cut if slipping) | Eng | S | No | Yes | Not started | 0% |  | 2026-08-11 | 2026-08-12
M2 | M2-6 | Coordinator login-raise path | In-app raise; depends on v2 role model | Eng | M | No | Fast-follow | Blocked | 0% |  |  |  |  | V2-P1, V2-P3
M3 | V2-P1 | Phase 1 - Additive schema | child, child_member, subscription tables + backfill | Eng | M | No | No | Not started | 0% |  | 2026-09-01 | 2026-09-05
M3 | V2-P2 | Phase 2 - child_id on data tables | Add child_id everywhere + backfill + dual-read | Eng | M | No | No | Not started | 0% |  | 2026-09-08 | 2026-09-12 |  | V2-P1
M3 | V2-P3 | Phase 3 - Active-child app layer | Context + header switcher; data-layer cutover (~80 calls) | Eng | L | No | No | Not started | 0% |  | 2026-09-15 | 2026-09-26 |  | V2-P2
M3 | V2-P4 | Phase 4 - Emergency tie-in + coordinator login | Coordinator logged-in raise; break-glass wiring | Eng | M | No | No | Not started | 0% |  | 2026-09-29 | 2026-10-03 |  | V2-P3
M3 | V2-P5 | Phase 5 - Caregiver/coordinator dashboards | Logged-in helper dashboards (per-child cards) | Eng | M | No | No | Not started | 0% |  | 2026-10-06 | 2026-10-10 |  | V2-P3
M3 | V2-P6 | Phase 6 - Subscription gating | Entitlement flag (FREE_LAUNCH) + paywall UI | Eng | M | No | No | Not started | 0% |  | 2026-10-13 | 2026-10-17 |  | V2-P1
M3 | V2-P7 | Phase 7 - RLS cutover | Membership-based RLS; retire user_id UNIQUE | Eng | M | No | No | Not started | 0% |  | 2026-10-20 | 2026-10-24 |  | V2-P2
M3 | V2-P8 | Phase 8 - Razorpay integration | Payments + webhooks; only when pricing turns on | Eng | M | No | No | Not started | 0% |  |  |  |  | V2-P6

## Legend
Key | Meaning
M0 — Repo clean-up | 10 Jul gate: clean codebase, all commits on Rituja, migrations live, clean git status. Blocks M1.
KEY DATE — 15 Aug 2026 | Public launch (Independence Day) = M1 + the M2 free emergency wedge. Date-driven: cut scope, not the date.
15-Aug scope = Yes | Must ship for the 15 Aug launch
15-Aug scope = Fast-follow | Ships shortly after launch
15-Aug scope = No | Post-launch (Version 2, Sep-Oct)
Effort — S / M / L / XL | Small (hrs-1 day) / Medium (days) / Large (1-2 wks) / Extra large (multi-week)
Status | Not started / In progress / Blocked / Done
Launch gate = Yes | Hard gate — must be done before any public launch
M1 — MVP launch | Existing full plan, stabilized & legally launchable (free); internally ready ~25 Jul
M2 — Full product | M1 + the freemium 10-minute emergency wedge; public launch 15 Aug
M3 — Version 2 | Person/child/role redesign, multi-child, subscription infra; ~late Oct
Overdue rows | A Due date in the past with Status not Done is highlighted red
Source of truth | docs/PROJECT_PLAN.md and docs/REDESIGN_PLAN.md
Pricing | Free at launch behind the FREE_LAUNCH flag; the eventual subscription price is the only undecided item
Pace assumption | Dates assume part-time solo + AI. Full-time ~halves the calendar; weekends-only ~1.5-2x.